## Sheet1
Defect #	Status	Raised By	Tested on Version	TestCase Id	Steps to Reproduce	Expected Results	Actual Results	Priority	Severity
1	Open	Rehab Elashri	v3	SM6	1) Click on Delete Account 2) Enter required fields 3) Submit	1) A pop - up "Do you really want to delete this account?"	No confirmation message shown	Low	Low
2	Open	Rehab Elashri	v3	SM11	1) Click on Delete Customer 2) Enter Customer id 3) Submit	1) A pop - up "Do you really want to delete this customer?"	No confirmation message shown	Low	Low
3	Open	Rehab Elashri	v3	SM14	1) Click on Edit Customer 2) Enter Customer id 3) Submit	1) A pop - up "Customer does not exist" / 2) Redirect to Delete customer	alert " You are not authorise to edit this customer!" / redirect to delete customer page	Low	Low
4	Open	Rehab Elashri	v3	SM15	1) Click on Edit Customer 2) Enter Customer id 3) Submit	1) A pop - up "Customer does not exist" / 2) Redirect to Delete customer	alert " You are not authorise to delete this account!" / redirect to delete customer page	Low	Low
5	Open	Rehab Elashri	v3	SM17	1) Execute the above test case / 2) Refresh Fund Transfer detail page	Page should redirect to fund transfer page	Not redirecting to fund transfer page on clicking refresh button / on checking ministatement it is observed that transfer is done twice	High	High
6	Open	Rehab Elashri	v3	SM18	1) Click on Mini Statement / 2) Enter all required fields / 3) Submit	Statement should show above transactions	blank page	High	High
7	Open	Rehab Elashri	v3	SM19	1) Click on Fund Transfer / 2) Enter all required fields / 3) Submit	1) A pop - up " Account # does not exist"	1) A pop up "No details found for this account!!"	Medium	Low
8	Open	Rehab Elashri	v3	SM20	1) Click on Fund Transfer / 2) Enter all required fields / 3) Submit	1) A pop up "You are not authorize to Transfer Funds from this account!!"	1) A pop up "No details found for this account!!"	Medium	Low
9	Open	Rehab Elashri	v3	SM21	1) Click on Fund Transfer / 2) Enter all required fields / 3) Submit	1) A pop up "Payers account No and Payees account No Must Not be Same!!!"	No pop up and fund transfer sucessful or for non existing customer pop up "No details found for this account!!" is shown	Medium	Low
10	Open	Rehab Elashri	v3	SM24	1) Click on Deposit / 2) Enter all required fields / 3) Submit	1) Message - "Transaction details of Deposit for Account xyz" / 2) Details of Deposit	This page isn’t working / demo.guru99.com is currently unable to handle this request. / HTTP ERROR 500	High	High
11	Open	Rehab Elashri	v3	SM25	1) Refresh Deposit detail Page	Page should redirect to Deposit Page	Not redirecting to deposite page on clicking refresh button	High	High
12	Open	Rehab Elashri	v3	SM26	1) Determine balance in account / Click on Withdrawal / 2) Enter all required fields / 3) Submit	1) Message - "Transaction details of Withdrawal for Account xyz" / 2) Details of withdrawal	This page isn’t working / demo.guru99.com is currently unable to handle this request. / HTTP ERROR 500	High	High
13	Open	Rehab Elashri	v3	SM27	1)Click on Withdrawal / 2) Enter all required fields / 3) Submit	An Error message "Transaction failed account balance is low !!"	This page isn’t working / demo.guru99.com is currently unable to handle this request. / HTTP ERROR 500	High	High
14	Open	Rehab Elashri	v3	SM28	1) Click on Ministatement / 2) Enter all required fields / 3) Submit	Details of withdrawal done in above test case	blank page	High	High
15	Open	Rehab Elashri	v3	SM29	1) Click on Balance enquiry / 2) Enter all required fields / 3) Submit	Details of Balance (check deduction in balance)	blank page	High	High
16	Open	Rehab Elashri	v3	SM30	1) Click on customized Statement / 2) Enter all required fields / 3) Submit	Details of transactions done in above test case must be shown	blank page	High	High
17	Open	Rehab Elashri	v3	SM31	1) Click on Customized statement / 2) Enter all required fields / 3) Submit	1) pop - up "From date field should be lower than to date field"	blank page	High	High
18	Open	Rehab Elashri	v3	SM32	1) Click on Customized statement / 2) Enter all required fields / 3) Submit	1) Message - "Transaction Details for Account No From Date xyz to abc" / 2) Details of customized statemet	blank page	High	High
19	Open	Rehab Elashri	v3	SM33	1) Click on Edit acount / 2) Enter all required fields / 3) Submit	1) Details of updated account must be shown	This page isn’t working / demo.guru99.com is currently unable to handle this request. / HTTP ERROR 500	High	High
20	Open	Rehab Elashri	v3	SC5	1) Click on Balance enquiry / 2) Enter wrong account number which is not associated with customer / 3) Submit	Display alert message " You are not authorize to get Balance details of this account!! "	You can see balance of any account	Medium	Low
21	Open	Rehab Elashri	v3	SC9	1) Refresh Fund Transfer detail Page shown in above test case	Redirect to Fund Transfer input Page	Not redirecting and fund is transfer again	High	High
22	Open	Rehab Elashri	v3	SC11	1) Click on Fund Transfer / 2) Enter wrong Payer account number which is not associated with customer / 3) Submit	Display alert messsage "You are not authorize to Transfer Funds from this account!! "	Not displaying alert message and transfers the fund successful	High	High
23	Open	Rehab Elashri	v3	SC12	1) Click on Fund Transfer / 2) Enter wrong Payer or Payees account number which is not available in database / 3) Submit	Display alert messsage " Account ### does not exist!!! "	Display alert messsage " No details found for this accounts !!! "	High	High
24	Open	Rehab Elashri	v3	SC13	1) Click on Fund Transfer / 2) Enter same Payer account number and Payees account number which is available in database / 3) Submit	Display alert messsage " Payers account No and Payees account No Must Not be Same!!! "	No pop up and fund transfer sucessful or for non existing customer pop up "No details found for this account!!" is shown	High	Medium
25	Open	Rehab Elashri	v3	SC14	1) Click on Mini Statement / 2) Enter all required fields / 3) Submit	Display alert messsage " You are not authorize to generate statement of this Account!! "	Ministatement is generated for any account that exists in database	High	Medium
26	Open	Rehab Elashri	v3	SC16	1) Click on customize statement / 2) Enter all required fields / 3) Submit	Display alert messsage " You are not authorize to generate statement of this Account!! "	Customized statement is generated for any account that exists in database	High	Medium
27	Open	Rehab Elashri	v3	SC18	1) Click on customize statement / 2) Enter all required fields / 3) Submit	Display alert messsage " FromDate field should be lower than ToDate field!!"	Display alert messsage " No details found for this accounts !!! "	High	Medium
28	Open	Rehab Elashri	v3	WS5	1) Enter a value in Account Number Field in URL which is exist in database / 2) Press Enter	A Success message with mini statement in the json format should be displayed	Json format fail	High	Medium
29	Open	Rehab Elashri	v3	WS6	1) Do not enter a value in account numberin URL	An error in message "No Data " should be displayed in json format	Data is shown	High	Medium